Kennet Shopping Centre strip out plan in date order, RF version.

19th Aug 2025

This list goes along side the timeline for VP spreadsheet by RF and is a moving entity. This is due to the possibility for all units to be returned early or be occupied.

Ready to go now, as of 19th August 25 –

- 4a Mall, former nightclub

- 25 Mall

- 141 Bartholomew Street

October –

- Kiosk 4

- 139 Bartholomew Street

- 44/48 Mall

- 17 Market Place

November –

- 20 Mall

- 28 Mall

- 29/30 Cheap Street

December –

- V5

- 35a Mall

- 33 Mall

January 26 –

- Kiosk 10

- 25/27 & 28 Cheap Street

- 143/145 Bartholomew Street

- 19 Market Place

- 3a Market Place

- 40/42 Mall

- 31 Mall

- 27/29 Mall

- 26 Mall

- 24 Mall

- 23 Mall

- 22 Mall

- 19 Mall

- 16 Mall

- 13/17 Mall

- 5 Mall

February 26 –

- 1/3 Mall

- 2 Mall

- 4 Mall

- 6 Mall

- 7/9 Mall

- 11 Mall

- 21 Mall

- 30/32 Mall

- 34 Mall

- 36 Mall

- 38 Mall

- 38a Mall

- 50 Mall

- 5 Market Place

- 7 Market Place

- 9 Market Place

- 17a Market Place

- 24 Cheap Street

- Kiosk 1

- Kiosk 6/8

- Kiosk 12

The following units could be done together due to their proximity and dates coinciding with others –

October –

141 and 139 Bartholomew Street, 44/48 Mall, 25 Mall and 17 Market Place. Compound at the North part of the deck

November –

20 Mall, 28 Mall and 29/30 Cheap Street. Compound near the entrance barrier and offices, south part of the deck

December –

33 Mall and Kiosk 4 (via 33 Mall) Compound near the rear of Unit 6 or entrance barriers as November, both South part of the deck

January 26 –

5 Mall, 13/17 Mall, 19 Mall, 23 Mall, 31 Mall, 27/29 Mall, 143/145 Bartholomew Street. Also, 16 Mall, 22 Mall, 24 Mall, 26 Mall and 25/27/28 Cheap Street. Compound near the centre of the deck, or we use the same compounds as North or south parts of the deck

Kiosk 10 (Small) via 33 Mall

19 Market Place, 3a Market Place and 40/42 Mall. Compound to be near centre of deck

February 26 –

All other units can now be stripped out, compounds could be in various places across the deck. Access may need to be granted to the three public houses, this is being investigated. Remaining units are –

South part of the deck –

1/3 Mall, 2 Mall, 4 Mall, 6 Mall, 7/9 Mall, 11 Mall, 24 Cheap Street,

Middle part of the deck –

21 Mall, 30/32 Mall, 34 Mall, 36 Mall, 38 Mall, 38a Mall, 5 Market Place, 7 Market Place, 9 Market Place,

North part of the deck –

50 Mall, 17a Market Place, Kiosk 1, Kiosk 6/8 and Kiosk 12